## Fall 2016 Tentative Schedule
| Week # | Date | Sprint Day # | Meeting Room | Tasks
0 | 1 | 2016-08-22 | 1 |  | Preparation Tasks (see welcome post and the Task Desciptions tab); Sync Your LinkedIn Account;
|  | 2016-08-23 | 2 | In Person/Online | Learn the existing project; Read the documents; Watch the videos; Play with the existing software solution; Rank Proposed Projects; Accept Project Assignment;
|  | 2016-08-24 | 3 | In Person/Online | Collect User Stories; Create Project Backlog;
|  | 2016-08-25 | 4 | In Person/Online | Initial Requirement Analysis; Initial Feasibility Study; Initial System Design; all to be reflected in the Project Documentation file and be refined over time.
|  | 2016-08-26 | 5 | In Person/Online | Setup Development Environment; Initial Project Plan; Sprint Planning; to be reflected in the Project Documentation file and be refined over time.
1 | 2 | 2016-08-29 | 1 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-08-30 | 2 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-08-31 | 3 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-01 | 4 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-02 | 5 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
| 3 | 2016-09-05 | 6 | Holiday | Labor Day Holiday (University Closed)
|  | 2016-09-06 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-07 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-08 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-09 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
2 | 4 | 2016-09-12 | 1 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation) (Feedback & Grading Meeting - Online) (Demo, mingle, gtihub, code, document, diagrams, meeting minutes, time card and schedule)
|  | 2016-09-13 | 2 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-14 | 3 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-15 | 4 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-16 | 5 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
| 5 | 2016-09-19 | 6 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-20 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-21 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-22 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-23 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
3 | 6 | 2016-09-26 | 1 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation) (Feedback & Grading Meeting - Online) (Demo, mingle, gtihub, code, document, diagrams, meeting minutes, time card and schedule)(formal)
|  | 2016-09-27 | 2 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-28 | 3 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-29 | 4 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-09-30 | 5 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
| 7 | 2016-10-03 | 6 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-04 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-05 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-06 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-07 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
4 | 8 | 2016-10-10 | 1 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation) (5-10 minutes video of Demo, mingle, gtihub, code, document, diagrams, meeting minutes, time card and schedule) (It has to be uploaded to YouTube using the account provided to you. Please create a playlist for your team))
|  | 2016-10-11 | 2 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-12 | 3 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-13 | 4 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-14 | 5 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
| 9 | 2016-10-17 | 6 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-18 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-19 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-20 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-21 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
5 | 10 | 2016-10-24 | 1 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation) (Feedback & Grading Meeting - Online) (Demo, mingle, gtihub, code, document, diagrams, meeting minutes, time card and schedule)(formal)
|  | 2016-10-25 | 2 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-26 | 3 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-27 | 4 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-10-28 | 5 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
| 11 | 2016-10-31 | 6 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-11-01 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-11-02 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-11-03 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-11-04 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
6 | 12 | 2016-11-07 | 1 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation) (Feedback & Grading Meeting - Online) (Demo, mingle, gtihub, code, document, diagrams, meeting minutes, time card and schedule)
|  | 2016-11-08 | 2 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-11-09 | 3 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-11-10 | 4 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-11-11 | 5 | Holiday | Veteran's Day Holiday (University Closed)
| 13 | 2016-11-14 | 6 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-11-15 | 7 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation)
|  | 2016-11-16 | 8 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation) Wrapping up
|  | 2016-11-17 | 9 | In Person/Online | Daily Scrum; Working on one user story at a time (feasibility study, requirement analysis, design, development, testing, integration, validation) Wrapping up
|  | 2016-11-18 | 10 | In Person/Online | Daily Scrum; Finish up remaining work; Sprint Review; Sprint Retrospective; Sprint Planning;
7 | 14 | 2016-11-21 | 1 | In Person/Online | Wrapping up. You need to create a powerpoint (one per team). (I will provide you a template)
|  | 2016-11-22 | 2 | In Person/Online | You need to create an individual poster. (I will provide you a template)
|  | 2016-11-23 | 3 | In Person/Online | You need to create your final document (one per team). (I will provide you a template) . You need to upload your poster and powerpoint in the google drive (in poster&powerpoint&final document folder) , so i can check them and give you feedback.
|  | 2016-11-24 | 4 | Holiday | Thanksgiving Holiday (University Closed)
|  | 2016-11-25 | 5 | Holiday | Thanksgiving Holiday (University Closed)
| 15 | 2016-11-28 | 6 | Poster Due | On Monday, you need to submit your individual poster. The posters are due by 5 pm on Monday. Submit your poster using the link provided to you under Deliverables section in your Moodle course. (If you design your poster with google slide, please double check your poster with Microsoft powerpoint too). We will print them and we bring them to the showcase with easels.
|  | 2016-11-29 | 7 | In Person/Online | On Tuesday, you need to have your final document in the google drive. (one per team) (due by 5 pm)
|  | 2016-11-30 | 8 | In Person/Online | On Wednesday, you need to upload your final powerpoint in the google drive. (due by 5 pm)
|  | 2016-12-01 | 9 | In Person/Online | On Thursday, you need to practice your poster presentation for audience and judges. It would be great if each team print one copy of the final document for the showcase and everyone brings several copies of his/her resume.
|  | 2016-12-02 | 10 | Sowcase | On Friday (4pm-9.30 pm) - 4pm : Students need to be in ECS - 4:00pm-4:30pm: Group photo on ECS stairs - 4:30pm-5:30pm: Students need to be in PG6-105 for Surveys. - 5:30pm-6:10pm: Students need to help to move chairs from 116 to 122 and then prepare their stations in PG6-116 - 6:30pm: Welcome speech in PG6 lobby. - 6:30pm-9pm: Showcase in PG6 116. - 9pm-9.30pm: Students MUST help to move posters back to ECS and chairs from 112 to 116
8 | 16 | 2016-12-05 | 1 | In Person/Online | On Monday, you need to develop the Introductory Video (teamwork). The videos are due by 5 pm. You need to upload it into a YouTube channel that i will provide to you.(You need to create a playlist and this video will be the first video of your playlist)
|  | 2016-12-06 | 2 | In Person/Online | On Tuesday, you need to develop the Tutorial Video for Each Actor of Your System (one video per actor) (teamwork). The videos are due by 5 pm.
|  | 2016-12-07 | 3 | In Person/Online | On Wednesday, you need to develop the Installation & Maintenance Video (teamwork). The videos are due by 5 pm.
|  | 2016-12-08 | 4 | In Person/Online | On Thursday, you need to develop the Shortcomings & Wishlist Video (teamwork). The videos are due by 5 pm.
|  | 2016-12-09 | 5 | Final Deliverables Due | On Friday, you need to do any final touches to all the project documentations . You must download a Zip file from your most updated GitHub repository. (I will provide you the guideline for the Github). Upload your zip file using the link provided to you under Deliverables section in your Moodle course. The Final Deliverable is due by 5 pm .
Formulas:
Date = [Date, row above]+1