## Sheet1
2016-11-21 | In Person/Online | Wrapping up. You need to create a powerpoint (one per team). (I will provide you a template)
2016-11-22 | In Person/Online | You need to create an individual poster. (I will provide you a template)
2016-11-23 | In Person/Online | You need to create your final document (one per team). (I will provide you a template) . You need to upload your poster and powerpoint in the google drive (in poster&powerpoint&final document folder) , so i can check them and give you feedback.
2016-11-24 | Holiday | Thanksgiving Holiday (University Closed)
2016-11-25 | Holiday | Thanksgiving Holiday (University Closed)
2016-11-28 | Poster Due | On Monday, you need to submit your individual poster. The posters are due by 5 pm on Monday. Submit your poster using the link provided to you under Deliverables section in your Moodle course. (If you design your poster with google slide, please double check your poster with Microsoft powerpoint too). We will print them and we bring them to the showcase with easels.
2016-11-29 | In Person/Online | On Tuesday, you need to have your final document in the google drive. (one per team) (due by 5 pm)
2016-11-30 | In Person/Online | On Wednesday, you need to upload your final powerpoint in the google drive. (due by 5 pm)
2016-12-01 | In Person/Online | On Thursday, you need to practice your poster presentation for audience and judges. It would be great if each team print one copy of the final document for the showcase and everyone brings several copies of his/her resume.
2016-12-02 | Showcase | On Friday (4pm-9.30 pm) - 4pm : Students need to be in ECS - 4:00pm-4:30pm: Group photo on ECS stairs - 4:30pm-5:30pm: Students need to be in PG6-105 for Surveys. - 5:30pm-6:10pm: Students need to help to move chairs from 116 to 122 and then prepare their stations in PG6-116 - 6:30pm: Welcome speech in PG6 lobby. - 6:30pm-9pm: Showcase in PG6 116. - 9pm-9.30pm: Students MUST help to move posters back to ECS and chairs from 112 to 116
2016-12-05 | In Person/Online | On Monday, you need to develop the Introductory Video (teamwork). The videos are due by 5 pm. You need to upload it into a YouTube channel that i will provide to you.(You need to create a playlist and this video will be the first video of your playlist)
2016-12-06 | In Person/Online | On Tuesday, you need to develop the Tutorial Video for Each Actor of Your System (one video per actor) (teamwork). The videos are due by 5 pm.
2016-12-07 | In Person/Online | On Wednesday, you need to develop the Installation & Maintenance Video (teamwork). The videos are due by 5 pm.
2016-12-08 | In Person/Online | On Thursday, you need to develop the Shortcomings & Wishlist Video (teamwork). The videos are due by 5 pm.
2016-12-09 | Final Deliverables Due | On Friday, you need to do any final touches to all the project documentations . You must download a Zip file from your most updated GitHub repository. (I will provide you the guideline for the Github). Upload your zip file using the link provided to you under Deliverables section in your Moodle course. The Final Deliverable is due by 5 pm .